## Step1-Overview
Here we list down the various Epics that define the product to be made. Make sure there are enough Epics to give a comprehensive idea of what is required to achieve your product.
Epic
Player
Enemy
Boss
Level Design
Collision
Drop
Game State Management
Audio
Graphic
Camera
Buff
Defense Target
Defense Tactics
Pathfinding Algorithm

## Step2-Task Backlog
Instructions
Here we list down all the tasks required to achieve our goal for the project. Use the Epics listed in Step1-Overview to come up with these tasks. All Epics should have tasks listed to achieve that Epic. Rank each task with a Priority. Each "Must Have" task needs to be assgined to someone for completion. Add names in the table of Step3-Budgeting and the assignee column will have a dropdown list for you to pick from. "Week" refers to the week the task should be started and finished. Estimate the number of hours the task might require and always set which week this task is to be completed by. Everyone can only commit a certain number of hours each week. Make sure that the total time for all tasks in a week does not exceed that commitment. When a task is completed, the Hours Estimate will be interpreted as the time taken to actually finish the task. If a task does not belong to any Epic, leave that part empty for that task.
Epic | Priority | Task | Description | Hours Estimate | Week | Assignee | Type | Completed?
Boss | Must Have | Boss spawning logic | Boss appearing and spawn from left when player reaches the wave | 1 | 8 | Dalton | Code | Yes
Boss | Must Have | Boss attack and movement logic | Bosses are able to move in all 2D directions, but will prioritize player instead of the chocolate. Destroy barriers upon contact. | 2 | 8 | Dalton | Code | Yes
Enemy | Must Have | Health and damage system (enemy) | System to manage enemies taking damage from bullets. All damage and health will be easy to manage integers. | 2 | 8 | Zong Han | Code | Yes
Graphic | Must Have | Health Bar Display | Health bar UI to display the health of entity on the map. | 2 | 8 | Zong Han | Code | Yes
Enemy | Must Have | Enemy spawning logic | Enemies will spawn randomly on the left side of the map | 2 | 8 | Zong Han | Code | Yes
Collision | Must Have | Hitboxes | Add hitboxes for both player and enemies. | 2 | 8 | Fadzly | Code | Yes
Collision | Must Have | Circle-Circle collision | Hit test between circles. | 0.5 | 8 | Fadzly | Code | Yes
Collision | Must Have | Boundary collision | Hit test between hit-boxes and boundary. | 1 | 8 | Fadzly | Code | Yes
Collision | Must Have | Point-Circle collision | Hit test between points and circles. | 0.5 | 8 | Fadzly | Code | Yes
Collision | Must Have | Point-Rectangle collision | Hit test between points and rectangles. | 0.5 | 8 | Fadzly | Code | Yes
Collision | Must Have | Circle-Rectangle collision | Hit test between rectangles and circles. | 1 | 8 | Fadzly | Code | Yes
Collision | Must Have | Rectangle-Rectangle collision | Hit test between rectangles. | 2 | 8 | Fadzly | Code | Yes
Game State Management | Must Have | Main Menu | Main menu user interface and interaction. Should have - Play, options, exit. | 0.5 | 8 | Fadzly | Code | Yes
Player | Must Have | Ability to dash | Player character can quickly reposition in any directions a short distance when spacebar is pressed. | 2 | 8 | Dalton | Code | Yes
Player | Must Have | Player basic movement | Player character to move in all 2D directions | 2 | 8 | Dalton | Code | Yes
Boss | Must Have | Health and damage system (boss) | System to manage boss taking damage from player character. All damage and health will be easy to manage integers. | 0.5 | 9 | Fadzly | Code | Yes
Buff | Must Have | Buff meter | Meter will be gained after an enemy is killed. | 3 | 9 | Dalton | Code | Yes
Enemy | Must Have | Enemy attack and movement logic | Enemies will prioritize moving towards chocolate, but if player is nearby in its direction, move towards player instead. Damage barricade if bump into | 4 | 9 | Zong Han | Code | Yes
Player | Must Have | Basic shooting | Player character shooting basic projectiles with circle hitbox. Controlled by mouse (aiming) - bullets will follow mouse click direction. | 3 | 9 | Zong Han | Code | Yes
Camera | Must Have | Horizontal panning and follows player | Camera follows player but pans horizontally. If boundary is reached, only the player can move until it is out of boundary. | 5 | 9 | Fadzly | Code | Yes
Defense Target | Must Have | Reviving player logic | Reduce health to revive player. | 1 | 9 | Fadzly | Code | Yes
Defense Target | Must Have | Health and damage system (defense target) | System to manage defense target taking damage from enemies. All damage and health will be easy to manage integers. | 1 | 9 | Fadzly | Code | Yes
Player | Must Have | Invincibility effect | Player becomes impervious to every damage for 1.5 seconds after getting hit. Represented by a flickering effect | 3 | 9 | Dalton | Code | Yes
Player | Must Have | Health and damage system (self) | System to manage player character taking damage from enemies. All damage and health will be easy to manage integers | 3 | 9 | Dalton | Code | Yes
Boss | Must Have | 1st Boss attack pattern | 1st boss will have charging attack which will charge and deal massive damage to player. | 6 | 10 | Fadzly | Code | Yes
Buff | Must Have | Upgrades | Upgrades increase player's stats such as health up, damage up, fire rate up, mobility up. Upgrades will be activated after buff gained. | 2 | 10 | Dalton | Code | Yes
Level Design | Must Have | Obstacles | Obstacles to block movement. | 2 | 10 | Zong Han | Code | Yes
Pathfinding Algorithm | Must Have | Grid system for map | Generate point nodes to form map grid | 2 | 10 | Zong Han | Code | Yes
Pathfinding Algorithm | Must Have | Connection of nodes | Connect neighbours for nodes to form path for AI | 2 | 10 | Zong Han | Code | Yes
Defense Tactics | Must Have | Shooting system (Allies) | Allies will shoot bullets to direction of nearest enemies. All damage and will be easy to manage integers. | 2 | 10 | Dalton | Code | Yes
Defense Tactics | Must Have | Allies insert | Spawning attacking NPCs that help to defend chocolate with a specific time limit. Each wave can only add one allies... | 2 | 10 | Dalton | Code | Yes
Defense Tactics | Must Have | Health system (Barricades) | System to manage barricades taking damage from enemies. All health will be easy to manage integers. | 2 | 10 | Dalton | Code | Yes
Defense Tactics | Must Have | Barricades insert | To place barricades to block enemy's path and defend against enemy projectiles (if any). | 2 | 10 | Dalton | Code | Yes
Pathfinding Algorithm | Must Have | Astar Pathfinding | Implement astar pathfinding to find the shortest path between two nodes. | 4 | 10 | Zong Han | Code | Yes
Level Design | Must Have | Design of level 1 | Placing of obstacles to form the overall layout of level 1 | 1 | 10 | Fadzly | Level | Yes
Buff | Must Have | Reflective Foil (Timer) | Invulnerability mode for choco shooter. Reflect damage incurred to player back to enemy for short time period. | 1 | 11 | Zong Han | Code | Yes
Buff | Must Have | Fast Shots (Timer) | Double the firing rate of player. | 0.5 | 11 | Zong Han | Code | Yes
Game State Management | Must Have | Options Menu | Options menu user interface and interaction. Should have - resolution, volume | 2 | 11 | Fadzly | Code | Yes
Game State Management | Must Have | Pause Menu | Pause menu user interface and interaction. Pause menu contains resume, options, exit. | 2 | 11 | Dalton | Code | Yes
Buff | Must Have | Smart Pistol (Timer) | Player fired shots follow target enemies. Bullets will have a radar that will follows the detected enemies. | 1 | 11 | Zong Han | Code | Yes
Graphic | Must Have | Normal / boss wave indicator | Visual cues to alert player when enemy waves or boss is approaching | 1.5 | 11 | Fadzly | Code | Yes
Buff | Must Have | Player Heal | Recovers player health. | 0.5 | 11 | Zong Han | Code | Yes
Buff | Must Have | Frozing Shots (Timer) | Shoot projectiles which can slow down enemies. | 1 | 11 | Zong Han | Code | Yes
Buff | Must Have | Buff Activation | Player can activate and apply buffs from buff slots by pressing number button. | 3 | 11 | Zong Han | Code | Yes
Audio | Must Have | Function to manage audio | Create a function for other files to be able to call and use different audio easily | 1 | 12 | Fadzly | Code | Yes
Audio | Must Have | General SFX | General sounds that are not part of the UI (firing, impact, death etc) | 0.5 | 12 | Fadzly | Audio | Yes
Audio | Must Have | UI SFX | UI sounds. | 0.5 | 12 | Fadzly | Audio | Yes
Audio | Should Have | Music composition | Music for main menu and/or the game scene. | 0.5 | 12 | Fadzly | Audio | Yes
Graphic | Must Have | Entity sprites | Images of player, enemies, and defense target etc | 3 | 12 | Dalton | Art | Yes
Graphic | Must Have | Level backgrounds | Graphic background for level map | 4 | 12 | Fadzly | Art | Yes
Graphic | Must Have | Walking animation | Encompasses all walking animation of enemies and choco shooter | 3 | 12 | Dalton | Code | Yes
Graphic | Must Have | General UI elements design | Buttons, sliders, etc | 5 | 12 | Fadzly | Code | Yes
Graphic | Must Have | Buff icons | Images of buffs for better user experience (for example 3 active buffs in the active slots will need something to represent them) | 3 | 12 | Dalton | Art | Yes
Buff | Must Have | Buff display | Buff display in the center of the screen and move to stay at a position after that. | 3 | 12 | Zong Han | Code | Yes
Buff | Must Have | Single-use active buffs | Player loses active buff when time limit of activated buff reached. Upgrades will not disappear. | 2 | 12 | Zong Han | Code | Yes
Game State Management | Must Have | Credits Menu | Credit state containing information of dev team. | 2 | 12 | Zong Han | Code | Yes
| Must Have | Weekly progress meeting | Weekly progress report and discussion on Teams. | 3 | ALL | Dalton | Admin | Yes
| Must Have | Weekly progress meeting | Weekly progress report and discussion on Teams. | 3 | ALL | Fadzly | Admin | Yes
| Must Have | Weekly progress meeting | Weekly progress report and discussion on Teams. | 3 | ALL | Zong Han | Admin | Yes
Player | Won't Have | Charged shot | An alternate firing mode by holding down firing button then releasing after a certain amount of time. This projectile will deal more damage (and other effects depending on enemy). Activate in shop using currencies. |  |  |  | Code
Player | Won't Have | Rage mode | Sacrifice health of player to power up. Activate in shop using currencies. |  |  |  | Code
Enemy | Won't Have | Melee enemy dash to attack | Enemies will dash towards nearby target. |  |  |  | Code
Boss | Won't Have | 2nd Boss attack pattern | (TBD) 2nd boss can attack in a way that is different from 1st boss |  |  |  | Code
Buff | Won't Have | Buffs choices | Player gains an option to choose one out of three possible random active buffs when meter is full. |  |  |  | Code
Buff | Won't Have | Makeshift Foil (Timer) | Grants the player extra health temporarily. |  |  |  | Code
Defense Tactics | Won't Have | Different Attacking Abilities (Allies) | A few different types of allies with different attacking abilities. |  |  |  | Code
Drop | Won't Have | Purchase mechanics | Currencies can be used to buy upgrades and buffs. |  |  |  | Code
Drop | Won't Have | In-game currency drop logic | Random drop by enemies, guaranteed drop by bosses |  |  |  | Code
Game State Management | Won't Have | Shop overlay | To purchase active buffs, passive buffs, NPCs and barriers.​ |  |  |  | Code
Game State Management | Won't Have | Stats interface overlay | To view current upgrades |  |  |  | Code
Graphic | Won't Have | Coin icon | Chocolate coin drops from enemies to be used in shop |  |  |  | Art
Graphic | Won't Have | On Hit Particle effect | Have a simple on-hit effect when there is a collision |  |  |  | Code
Graphic | Won't Have | Shop UI design | 2D art of the shop UI in game |  |  |  | Art
Graphic | Won't Have | Particle Effects | Playing of effects when doing actions or when collision happens |  |  |  | Art
Level Design | Won't Have | Design of level 2 | The overall layout of level 2 |  |  |  | Level
Level Design | Won't Have | Traps | Moving or static traps that will inflict damage to player upon contact. |  |  |  | Code

## Step3-Budgeting
Instructions
Here all members of the team declare their commitments to the project and check if the delegated workload is within what has been committed. At least 50% of the Planned Load needs to be Code tasks. If the given excel sheet formula does not auto-fill the hours from the Backlog correctly, students are to fill it in manually.
"Weekly Commitment" | Each student needs to declare the number of hours per week that they will work on the project. Every student has their own degree of ability to cope with this class and the other classes. An honest and realistic answer to this needs to be set, to better control the scope of the project and by extension, the scope of work needed to be done per individual.
"Total Commitment" | The product of Weekly Commitment and the number of weeks committed to working on this project. This will represent the total amount of work that can be done by the individual.
"Planned Load" | Total workload assigned to this individual. Only counting tasks that are Must Have. These should not exceed the total number hours stated in Total Commitment. There is an excel formula in that slot. Regardless if the formula works, the number in the cell must be reported correctly.
"Code Load" | Code Load should be more than or equal to half of the Planned Load. This is a class for Computer Science students, everyone needs to do that minimal amount of Code.
Student Name | Student DigiPen e-mail | Weekly Commitment | Total Commitment | Planned Load (Must haves) | Planned Code Load (Must haves) | Completed Load | Completed Code Load
Fadzly | muhammadnurfadzly.b@digipen.edu | 8 | 40 | 40 | 31 | 40.5 | 31
Zong Han | zonghan.law@digipen.edu | 8 | 40 | 40 | 37 | 40 | 37
Dalton | d.koh@digipen.edu | 8 | 40 | 40 | 31 | 40 | 31
| Team Totals | 24 | 120 | 120 | 99 | 120.5 | 99

## TaskTypes
Task Types | Description & Requirements | Requirements
Level | For tasks related to creating levels for the project. Ideally done without hardcoding all objects in the level within code. | @Must have a beginning and an end @Meaningful choices for the player to make @Clear objective
Art | For tasks related to creating visual art assets for the project. This includes fonts. Fonts : There are some license free fonts allowed for use. Refer to forum post. This should be kept to a minimum for RTIS and IMGD students. | @Refer to the EULA that you signed at the start of the semester @Do not use existing art assets even if they are "license free" @Tools used in the generation of art assets must be license and cost free
Audio | For tasks related to finding, creating and/or getting audio assets into the project. There are audio assets provided by the school via MetaDigger. Refer to forum post. The tasks related to coding an audio system to play audio assets should be under "Code". The audio system is a coded feature. | @Refer to the EULA that you signed at the start of the semester @Usage of existing audio assets allowed only for those found in the school's MetaDigger @Do not use external existing audio assets even if they are "license free", provided for or generated by tools @Recording your own audio, editting it with a free tool and using that asset is allowed
Code | For tasks related to feature implementation and code integration. Hardcoding levels and content for the game does not fall under this category. That would be under the task type of "Level" | @Feature functions as described and intended @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Bug Fix | For tasks related to fixing bugs that have been detected. Debugging is expected to be done during coding and development, but not all bugs would get detected during that phase. | @Symptoms identified with bugs gone @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Admin | For administrative tasks like: @Team Meetings @Presentation materials @Production documents @Marketing materials

## Priorities
Priorities | Brief | Completion
Must Have | Critical, cannot do without | Yes
Should Have | Important to the project but not vital | No
Could Have | Nice to have
Won't Have | Would not contribute to your project, can do without

## Plan Grading
Grading
Teams start with an "A" grade. Accumulated penalties will be applied to lower the grade. Teams do not need to fill this page. This page is only relevant for the very first plan submission.
Penalties | Penalty Range | Penalty Given | Feedback
Step 2 "Week" not filled with the relevant week numbers. | -1 per offending task
Assigned tasks leads to member/s exceeding their time budget. Example. Assignee commits 10 hours a week for 6 weeks. 61 hours of work were assigned. Penalty given. | -2 per offending member
Tasks are too vague. Tasks title and/or description does not sufficiently inform the assignee the scope of work required and/or begin work. | -1 per 10% of tasks
Tasks too large. Requires more than a week of the assignee's commitment. Break it down into smaller tasks. Should a task require more than a week of work, a team can be set back significantly if that task is not completed by the allocated date. Penalty is high to discourage this. | -1 per offending task
Missing data on any of the Step pages. | -1 per missing data field. A data field here is defined as a single excel cell.
Workload not well distributed. Difference between workloads between two or more members is greater than 20% of the workload done by the member with a smaller workload. | -1 to -4
Priorities and/or sequences of tasks work against the completion of the project. Includes but not limited to: - "Must Have" features left to the end of the production pipeline - Key features not labelled as "Must Have" - Tasks with pre-requisites are planned to be completed without the pre-requisites completed. | -1 to -4
| Total Penalty | 0
Final Grade